# RIOT Headbanger Rev A Engineering Dossier

Mono Class A headphone amplifier and preamplifier

This dossier records the current Rev A design, the evidence supplied with the KiCad engineering-review package, the remaining release blockers and the exact sequence for prototype bring-up. The board is routed and electrically checked, but it is not yet released for fabrication or headphone use.

# Release status

| Gate | Status | Evidence or next action |
| --- | --- | --- |
| Schematic ERC | Pass | 0 violations in KiCad 10.0.1. |
| PCB DRC | Pass | 0 violations and 0 unconnected items. |
| Schematic to PCB parity | Pass | 0 electrical differences; 115 classified non-electrical warnings. |
| Real-device DC validation | Open | Verify pinouts, JFET current and all bias nodes on the assembled board. |
| Thermal soak | Open | 60-minute test at +/-15 V; confirm bias settles and temperatures remain safe. |
| Protection validation | Open | Measure relay delay, DC trip and rail-loss response with real parts. |
| Load and stability test | Open | Oscilloscope test into 16 ohm non-inductive dummy load before headphones. |
| Fabrication release | Blocked | Release only after all staged prototype tests pass and are logged. |

# Architecture

J5 unbalanced input.

U310 and LSK170 all-JFET cascoded source follower.

C49/R38 AC coupling into the complementary EF2 stage.

KSC1845 and KSA992 drivers, BD139 VBE multiplier, KSC2690A/KSA1220A output pair.

Two series 4700 uF output capacitors with DC midpoint bias.

DC and rail-fault sensing with delayed 24 V Omron relay output.

On-board 18-0-18 VAC rectification, CRC filtering and LM317/LM337 +/-15 V regulation.

# Electrical targets and calculated performance

| Parameter | Current documented value |
| --- | --- |
| Supply rails | +15 V and -15 V regulated |
| Loaded voltage gain | Approximately 0.89 V/V |
| Input reference used in model | 2.5 Vrms at 1 kHz |
| Modelled output | 2.224 Vrms at J1 |
| Modelled power into 16 ohm | 0.309 W |
| Modelled load current | 139 mArms, 197 mA peak |
| Output coupling | Two 4700 uF capacitors in series; approximately 2350 uF effective |
| Output capacitor corner | Approximately 4.23 Hz into 16 ohm |
| EF2 idle-current target | Approximately 75 mA; acceptance 65-85 mA after warm-up |
| Emitter resistor adjustment | 35.25 mV across each 0.47 ohm resistor |
| CAPMID target | -9.5 V to -11.5 V before headphones |

# JFET front end

Q6/Q8 are U310 cascode devices and Q7/Q9 are LSK170 devices. The selected current is device-specific rather than a single assumed value.

| Device basis | FE current target | Modelled FE output | Modelled FE THD |
| --- | --- | --- | --- |
| Idss 3.35 mA, Vp 0.31 V | 1.45 mA | 2.480 Vrms | 0.0205% |
| Idss 5.5 mA, Vp 0.41 V | 2.30 mA | 2.483 Vrms | 0.0105% |

Set and verify current by measuring TP2-TP1 across R35, where 14.5 mV corresponds to 1.45 mA and 23.0 mV corresponds to 2.30 mA. These are generic-model calculations, not a substitute for measurements on the purchased devices.

# Thermal and mechanical requirements

Q3, Q5 and Q4 require close thermal contact on one shared, electrically insulated heatsink rated at 5 K/W or lower.

Q3 and Q4 tabs must be electrically isolated from the heatsink and from one another as required by their node potentials.

U3 and U4 require separate heatsinks; their tabs are at different electrical potentials.

The enclosure still requires a safe mains inlet, primary fuse, switch, protective earth and transformer mounting.

The circuit has no output short-circuit or over-current limiter. Do not hot-plug a connector that can short the output.

# Bring-up procedure

Verify the actual lead order and authenticity of U310, LSK170, KSC1845, KSA992, KSC2690A, KSA1220A and BD139.

Populate rectifiers, CRC network and regulators only. Use fused primary wiring and a current-limited AC source.

Set the regulators to +15.00 V and -15.00 V. Accept +/-0.10 V and less than 100 mV rail imbalance.

Load each rail at 120 mA for 30 minutes. Confirm regulation, temperature and absence of thermal shutdown.

Populate the JFET front end. Set the selected current and log source, drain, cascode-drain and BUF_OUT voltages.

Populate the EF2 without K1 or headphones. Start from a current-limited +/-5 V bench supply and increase in steps.

Set 35.25 mV across R11 and R12. The readings must agree within 5 mV.

Thermal-soak for 60 minutes at +/-15 V. Confirm 65-85 mA settled idle current, AMP_OUT within +/-100 mV and cases below 80 C.

Confirm CAPMID is -9.5 V to -11.5 V and J1 is below 10 mV DC after relay closure.

Test relay timing and DC protection with a dummy load, including +/-1 V forced faults and loss of either rail.

Use a 16 ohm, 5 W non-inductive dummy load and oscilloscope before any headphone connection.

Use a disposable 32 ohm headphone pair for the first listening test; the 15/16 ohm Ananda comes last.

# Validation evidence in the supplied package

design/ contains the active KiCad project, schematic sheets, PCB and project settings.

source_snapshot/ contains the recovered baseline before the final routing pass.

validation/ contains ERC, DRC, parity, BOM, connections, critical parts, board statistics, renders and generic simulation results.

The package includes a NOT RELEASED fabrication-review archive; it must remain treated as a review artifact, not a manufacturing release.

# Known risks and unresolved questions

Real-device pinouts, authenticity and semiconductor spread are not yet verified.

Generic transistor models do not establish distortion, stability or safe thermal behaviour.

Oscilloscope stability with a 15/16 ohm load and reactive headphone cable has not been tested.

Relay timing, trip threshold and rail-loss behaviour remain simulation-only until measured on the assembled board.

Shared output-heatsink mechanics and electrical insulation remain enclosure-level work.

The 115 parity warnings are classified as non-electrical, but the classification should be retained with the package.

# Where to resume

Do not reroute Rev A unless a genuine defect is found. The next engineering action is controlled prototype bring-up, beginning with regulator-only testing and real-device pinout verification. Append measured values to this dossier after each gate; do not rely on memory or chat history.

# Revision note

This dossier is based on RIOT_HEADBANGER_REV_A_ENGINEERING_REVIEW.zip supplied on 15 October 2026. It supersedes older Headbanger notes where they conflict with the current Rev A engineering review, especially the output-stage idle-current target.